## Overview
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
RETESTING RESULT
| FAILED TEST CASES IN BUILD 1 | FAILED TEST CASES FROM BUILD 1 IN BUILD 2 | FIX PERCANTAGE
Install and update the app | 0 | 0 | no
User Sign Up and Log in | 2 | 2 | 0
Functionality | 21 | 19 | 9
UI and Navigation check | 8 | 8 | 0
Compatibility check | 2 | 2 | 0
Interaction with the server | 0 | 0 | no
REGRESSION RESULT
| PASSED | FAILED | SKIPPED | TOTAL
Install and update the app | 6 | 0 | 0 | 6
User Sign Up and Log in | 11 | 2 | 0 | 13
Functionality | 32 | 8 | 13 | 53
UI and Navigation check | 13 | 8 | 0 | 21
Compatibility check | 3 | 0 | 2 | 5
Interaction with the server | 7 | 0 | 0 | 7
Report | The goal of the current testing phase is to verify a new mobile app build, test new functionality, check whether the reported bugs were fixed, and how the app behaves after these fixes. The majority of previously detected defects remain unresolved in the new build version, so the current build needs refinement. These defects impact the crucial app's functionality and as a result, the app doesn't meet the requirements and potential customers' expectations now. So, further attention should be paid to the reported defects to provide the user with more app features and a convenient user experience.

## Install and update the app
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Tyoe | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-101 | Regression testing | Install the app | Verify that the mobile application can be installed correctly and doesn't impact other apps and data. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready | 1. Open App Store (IOS) or Google Play (Android) 2. Enter 'Spaces by Wix' in a search bar 3. Tap 'Search' button on the keyboard 4. Find 'Spaces by Wix' app in apps list 5. Tap 'Spaces' icon to open app's page 6. Tap Install button 7. Verify that mobile app appeared on the Home screen | The application is successfully installed and is displayed on the device screen. Other applications and data are not impacted. | Passed
TC-102 | Regression testing | Launch the app | Verify that an application launches fast and without crashes. When user opens the app correct screens are displayed. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | 1. Find Spaces app on the device 2. Tap the app icon 3. Verify that the app is opened accurately | An application launches fast and without crashes. Spaces logo screen is displayed. Then authorization screen is automatically opened. | Passed
TC-103 | Regression testing | Minimize the app | Verify that an application can be minimized and no crashes occurs. The app remains in background. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. The application is launched 5. Skybot site is opened | IOS: 1. Tap left arrow at the upper left corner of the screen to exit from Skybot 2. Swipe up from the bottom of the screen to minimize the app/ Android: 1. Tap left arrow at the upper left corner of the screen to exit from Skybot 2. Tap "back" button from the lower navigation bar of the device to minimize the app. | Application is minimized but continue running in background. When user opens it again, the last screen is displayed. | Passed
TC-104 | Regression testing | Close the app | Verify that an application can be closed and is not running in background. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. The application is minimized | IOS: 1. Swipe up from the bottom of the screen 2. Find Spaces app 3. Swipe up from the bottom of the app tab Android: 1. Tap 'square' button at the lower leftt corner of the lower navigation bar of the device 2. Find Spaces tab 3. Swipe up from the bottom of the app tab | Application is closed and is not running in background. When user opens it again, the start logo screen is displayed. | Passed
TC-105 | Regression testing | Updating the application | Updating the application to a new version | 1. A device or emulator for testing is ready | 1.Open the Spaces app, go to "My profile", tap on "Help & feedback", tap on "About the Spaces by Wix" app and look at the app Version | The app has been successfully updated to the latest version. | Passed
|  |  |  | 2. The application is installed on the device | 2.Open the Play Market on your phone, search for "Spaces: Follow Businesses" and tap on it
|  |  |  | 3.The new version is available. | 3.Tap on "What's new" link and chek the latest version
4.If your application version is older than the version in Play Market, tap on the update button and update the app.
TC-106 | Regression testing | Uninstall the app | Verify that the mobile application can be uninstalled correctly. No other data and applications are deleted. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | IOS: 1. Find Spaces app on the device 2. Tap and hold the app icon 3. Tap 'Remove app' in the opened menu 4. Tap 'Delete app' in the opened window 5. Tap 'Delete' in the next opened window Android: 1. Find Spaces on the device (home screen or menu) 2. Tap and hold the app icon 3. Tap Uninstall from app info menu 4. Tap OK in the opened modal window | The application is successfully uninstalled and is not displayed on the device screen and in the app library. Other applications and data are not impacted. | Passed

## User Sign Up and Log in
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Type | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-201 | Regression testing | Sign Up with valid email and password | Verify that user can create a personal account using valid email and password. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app | 1. Open Spaces app 2. Tap Sign up 3. Tap Sign up with Email 4. Enter a valid email 5. Tap Continue 6. Enter a valid password in Password input field 7. Repeat an entered password in Confirm password input field 8. Tap Create password | User is successfully signed up in the app. He can access his personal account. | Passed
TC-202 | Regression testing | Sign Up with Google account | Verify that user can create a personal account using an existing Google account. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app 5. User has Google account | 1. Open Spaces app 2. Tap Sign up 3. Tap Continue with Google 4. Tap Continue in opened alert modal window 5. Select Google account 6. Tap Continue on the next screen | User is successfully signed up in the app. He can access his personal account. Name and email from Google account are displayed in the app. | Passed
TC-203 | Regression testing | Log in with valid email and password | Verify that user can log in to a personal account using valid email and password. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is not logged in | 1. Open Spaces app 2. Tap I already have a Wix account 3. Tap Login with Email 4. Enter a valid email 5. Tap Continue 6. Enter a valid password in Password input field 7. Tap Log In | User is successfully logged in the app. He can access his personal account. All previously saved data persists. | Passed
TC-204 | Regression testing | Log in with Google account | Verify that user can log in to a personal account using an existing Google account. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User has Google account 5. User is not logged in | 1. Open Spaces app 2. Tap I already have a Wix account 3. Tap Continue with Google 4. Tap Continue in opened alert modal window 5. Select Google account 6. Tap Continue on the next screen | User is successfully logged in the app. He can access his personal account. All previously saved data persists. | Passed
TC-205 | Regression testing | Restore password | Verify that user can restore an access to his personal account if he forgot the password. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is not logged in | 1. Open Spaces app 2. Tap I already have a Wix account 3. Tap Login with Email 4. Enter a valid email 5. Tap Continue 6. Tap Forgot your password 7. Tap Go to Email or open Email app on your device by yourself 8. Open an email with restoration link 9. Tap Change Password in opened email 10. Enter a new password 11. Confirm a new password in the next input field 12. Tap Save new Password | The password has been changed. User can login with new credentials. Old password can't be used to login. | Passed
TC-206 | Regression testing | Sign Up with invalid email | Verify that user can't sign up with invalid email. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app | 1. Open Spaces app 2. Tap Sign up 3. Tap Sign up with Email 4. Enter a valid email 5. Tap Continue | Error message 'Enter a valid email address' is displayed. User can't proceed further. | Passed
TC-207 | Regression testing | Sign Up with invalid password | Verify that user can't sign up with invalid password. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app | 1. Open Spaces app 2. Tap Sign up 3. Tap Sign up with Email 4. Enter a valid email 5. Tap Continue 6. Enter an invalid password in Password input field (less than 6 characters). 7.Repeat the еуіе by entering more than 100 characters in the Password input field. | Error message 'Password must have at least 6 characters' is displayed. User can't proceed further. | Passed
TC-208 | Regression testing | Log in with registered email and incorrect password | Verify that user can't log in to the personal account if password is incorrect. Verify that application responds with a generic error message regardless of whether the email or password is incorrect. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is not logged in | 1. Open Spaces app 2. Tap I already have a Wix account 3. Tap Login with Email 4. Enter a valid email 5. Tap Continue 6. Enter an incorrect password in Password input field 7. Tap Log In | Error message 'The Email or password is incorrect' is displayed. User can't proceed further. | Passed
TC-209 | Regression testing | Log out | Verify that user can log out from the personal account. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Spaces app 2. Tap My Profile icon at the left side of the application lower bar. 3. Scroll down the screen 4. Tap Log out 5. Tap Log out in the opened modal alert window | User is logged out from the account. Start screen for authentication is displayed. | Passed
TC-210 | Regression testing | Sign Up with registered email | Verify that already registered email can't be used for sign up process again and corresponding error message is displayed. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is not logged in | 1. Open Skybot in Spaces app 2. Tap Sign up 3. Tap Sign up with Email 4. Enter a previously registered email 5. Tap Continue | User can't sign up with a previously registered email. Alert window is displayed proposing user either cancel registration or login to the existing account. | Passed
TC-211 | Regression testing | Enter an incorrect password in confirm password field | Verify that user can't sign up if the repeated password doesn't match the previously entered. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app | 1. Open Skybot in Spaces app 2. Tap Sign up 3. Tap Sign up with Email 4. Enter a valid email 5. Tap Continue 6. Enter a valid password in Password input field 7. Enter another string in Confirm password input field 8. Tap Create password | User can't sign up, the error message 'Passwords don't match, try again' is displayed. | Passed
TC-212 | Retesting | Change password | Verify that user can change password in account settings. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Tap Change password 4. Enter an old password in the Old password input field 5. Enter a new password in the New password input field 6. Repeat a new password in the Confirm password input field 7. Tap Change password | A new password is set up and can be used to login. User has to login again if there are active sessions on the other devices. | Failed | The application doesn't provide the feature to change a password in settings. The user has to do this only through Restore password functionality.
TC-213 | Retesting | Login to the web portal via an account registered through the app | Verify that the app and the web are synchronized and if the user signs up in the app he can log in to the account in the web version. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app | 1. Open the web version of the portal Skybot 2. Press Log in button at the upper left of the page 3. Press Log in button (above Sign up options) 4. Press Log in with email button 5. Enter your previously registered email 6. Enter your password 7. Press Log in button | The user is successfully logged in to the eb version. He has access to his profile and all related data. | Failed | The web version doesn't recognize the user previously signed up via the app.

## Functionality
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Type | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-301 | Regression testing | Browse catalog | Verify that product catalog with all available goods is displayed and can be observed. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Scroll down the screen 4. Tap See all button 5. Verify that product cards in catalog comprises photo, model name, price, availability, and rating | Product catalog with all available goods is displayed. Catalog can be expanded to view all products. Photo, model name, price, availability, and rating are displayed. | Passed
TC-302 | Regression testing | Search by a valid query | Verify that certain product items can be searched. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap on the Search bar at the top of the catalog 4. Enter a query (model name) 5. Verify that search results correspond to the entered query | If searched product item exists in catalog, corresponding result is displayed. Only searched product item is shown. | Passed
TC-303 | Regression testing | Search by an invalid query | Verify that search is not conducted if query is less than 3 characters. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap on the Search bar at the top of the catalog 4. Enter a query that has less than 3 characters length | Message 'Enter 3 or more characters' is displayed. Search process is not being conducted. | Passed
TC-304 | Retesting | Filter by category | Verify that product items can be filtered by category. Verify that only certain product items are displayed if filter is applied. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap Filter icon at the upper right corner of the catalog 4. Tap Category 5. Tap Electric Scooters 6. Tap Show Items 7. Tap Filter icon at the upper right corner of the catalog 8. Enable In stock filter by switching toggle 9. Tap Show Items | User can filter items by category. When filter is applied, only corresponding items are displayed. If several filter are applied, items corresponding to each filter are displayed. Items quantity is displayed. | Failed | The result of filtering by category shows products that do not correspond to the selected category
TC-305 | Retesting | Filter by brand | Verify that product items can be filtered by brand. Verify that only certain product items are displayed if filter is applied. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap Filter icon at the upper right corner of the catalog 4. Tap Brand 5. Select any brand 6. Tap Show Items | User can filter items by brand. When filter is applied, only corresponding items are displayed. | Skipped | The brand filter is not available in version 2.0 of the application.
TC-306 | Retesting | Filter by price range | Verify that product items can be filtered by price. Verify that only certain product items are displayed if filter is applied. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap Filter icon at the upper right corner of the catalog 4. Tap Price 5. Enter price range 6. Tap Show Items | User can filter items by price. When filter is applied, only corresponding items are displayed. | Skipped | Filter by price is not implemented in version 2.0 of the application..
TC-307 | Retesting | Filter by rating | Verify that product items can be ratingby price. Verify that only certain product items are displayed if filter is applied. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap Filter icon at the upper right corner of the catalog 4. Tap Rating 5. Tap any rating value 6. Tap Show Items | User can filter items by rating. When filter is applied, only corresponding items are displayed. | Skipped | Filter by rating is not implemented in version 2.0 of the application..
TC-308 | Retesting | Sort items | Verify that product items are sorted according to the applied sort method. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap Sort 4. Select sort method 5. Verify that product items are sorted according to the applied method | Product items are sorted according to the applied sort method. | Skipped | Sorting is not implemented in version 2.0 of the application.
TC-309 | Regression testing | Filter by availability in stock | Verify that product items can be filtered by availability in stock. Verify that only certain product items are displayed if the filter is applied. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap Shop tab 3. Tap Filter icon at the upper right corner of the catalog 4. Enable In stock toggle 5. Tap Show Items 6. Ensure that only corresponding items are displayed and nothing is missed | Users can filter items by availability in stock. When the filter is applied, only corresponding items are displayed. No corresponding items are missed and no unexpected products appear. Items quantity is displayed. | Passed | Users can filter items by availability in stock. When the filter is applied, only corresponding items are displayed. No corresponding items are missed and no unexpected products appear. Items quantity is displayed.
TC-310 | Retesting | Verify product detail page | Verify that model name, SKU, available quantity in store, color options (if they exist), selected quantity, technical description, rating, reviews and images of the product are displayed on the screen. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Tap any product item 4. Scroll down the opened screen 5. Inspect what product details are displayed. | Model name, SKU, available quantity in store, color options (if they exist), selected quantity, technical description, rating, reviews and images of the product are displayed on the screen. | Failed | SKUs of product items don't have a readable consistent format (for all products). Wrong titles are used for some products (see the attachment). The wrong title and description are used for the Electric Skateboard product. No description is added to the Skybot Day-to-Day product The wrong description is added to Skybot Dualtron
TC-311 | Regression testing | Subscribe for product availability notifications | Verify that the user can subscribe to be notified when a product appears in stock. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. A product item is out of stock | 1. Open Skybot in Spaces app 2. Tap Shop tab 3. Scroll down the screen till product with Out of stock status 4. Tap the product 5. Tap Notify When Available 6. Enter a new email or leave the displayed email 7. Tap Submit | The submission snackbar is displayed at the bottom of the screen. The user is subscribed to the product availability notification. | Passed | The submission snackbar is displayed at the bottom of the screen. The user is subscribed to the product availability notification.
TC-312 | Regression testing | Share product via social media | Verify that product items can shared via social media. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop tab 3. Scroll down the screen 4. Tap See all button 5. Tap any product item 6. Tap Share icon at the upper right corner of the screen 7. Verify that user can copy link to share 8. Verify that user can share link directly to the certain social media | Product items can be shared via social media. | Passed
TC-313 | Retesting | Verify product recommendations | Verify that recommendations for the user are displayed and are based on his history (registered users only). | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. User has already viewed product items | 1. Open Skybot in Spaces app 2. Tap Shop if this tab is not opened 3. Scroll down the screen 4. Tap See all button 5. Verify that there is a separate category Recommendations for you | Based on the user's viewed products recommended product items are displayed. They are grouped in separate category. | Failed | Recommendations to the user are absent in the app.
TC-314 | Regression testing | Verify catalog correspondence in the app and the web version | Verify that the same products are displayed in both the app and web version. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in to the app 6. A web version is ready for testing | 1. Open Skybot in Spaces app 2. Tap Shop tab 3. Scroll down the screen and observe all products in the app 4. Open the web version of Skybot 5. Navigate to the Shop page 6. Scroll down the screen and observe all products in the web portal 7. Verify that the product list is the same in both mobile and web versions | The product catalog in the app conforms with the one in the web version. | Passed | The product catalog in the app conforms with the one in the web version.
TC-315 | Regression testing | Access cart as not logged in user | Verify that actions with cart are restricted until users are logged in. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not logged in | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen | Actions with cart are restricted until users are logged in. | Passed
TC-316 | Regression testing | Add product to cart | Verify that product items can be added to cart and saved for future purchase. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Scroll down to button See all 4. Tap See all 5. Open any product item 6. Tap Add to cart button 7. Tap View to open cart | Item is added to cart and correct quantity and price are displayed. | Passed | Item is added to cart and correct quantity and price are displayed.
TC-317 | Regression testing | Remove product from cart | Verify that product items can be removed from cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. At least 2 different product items are added to cart | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Remove from cart 5. Verify that products list and total price are updated 6. Swipe left the other selected product item to the left side of the screen 7. Verify that product item is deleted | Product item is deleted from cart. If there are other product items, they remain in cart and updated total price is displayed. If there are no other items, empty cart is displayed. | Passed | Product item is deleted from cart. If there are other product items, they remain in cart and updated total price is displayed. If there are no other items, empty cart is displayed.
TC-318 | Regression testing | Clear cart | Verify that there is an option to clear the entire cart at once. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. At least 2 different product items are added to cart | 1. Open Skybot in Spaces app 2. Tap Cart icon at the upper right corner of the screen 3. Tap 3 horizontal dots at the upper right corner of the screen 4. Tap Clear cart 5. Verify that all items are removed | The entire cart is cleared at once, no product items are remained regardless the quantity. | Passed
TC-319 | Regression testing | Change quantity of product on PDP | Verify that product item's quantity can be changed on the PDP before adding to cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Scroll down to button See all 4. Tap See all 5. Open any product item 6. Tap + button to increase quantity 7. Tap Add to cart button 8. Tap View to open cart | Defined item's quantity is added to cart and correct quantity and price are displayed. | Passed | Defined item's quantity is added to cart and correct quantity and price are displayed.
TC-320 | Regression testing | Change quantity of product in cart | Verify that product item's quantity can be changed in cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Change quantity 5. Enter new quantity 6. Tap Apply | Updated quantity and price are displayed after quantity change. | Passed | Updated quantity and price are displayed after quantity change.
TC-321 | Regression testing | View product item from cart | Verify that product detail page can be accessed from cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap View product | Product detail fullscreen modal window of the selected product item is opened. | Passed
TC-322 | Regression testing | Add a product item out of stock | Verify that product items out of stock can't be added to cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Scroll down to button See all 4. Tap See all 5. Open a product item out of stock 6. Verify that it is not possible to add a product to cart | It is not possible to add a product item if it is out of stock. | Passed
TC-323 | Retesting | Apply a promo code to order | Verify that user can apply a promo code to order. Order's price should be accurately updated. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Promo code 5. Enter a promo code in the input field 6. Tap Apply | Order's price is accurately updated when a valid promo code is applied. | Passed | "Order's price is accurately updated when a valid promo code is applied. $15.00 discount is applied to each product item in the cart."
TC-324 | Retesting | Apply an invalid promo code to order | Verify that invalid promo code can't be applied to the order and corresponding message is displayed. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open Skybot in Spaces app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Promo code 5. Enter an invalid promo code in the input field 6. Tap Apply | Invalid promo code is not applied and message 'Promo code isn't valid' is displayed. | Passed | Invalid promo code is not applied and message 'Promo code isn't valid' is displayed.
TC-325 | Regression testing | Add a note to order | Verify that user can add a note to order. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Note 5. Enter a note in the input field 6. Tap Apply | Note is added to the order and displayed on the screen. | Passed
TC-326 | Retesting | Add a note to order of max acceptable length | Verify that user can't add a note to order if it is beyond the acceptable limit (more than 1000 characters). | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open Skybot in Spaces app 2. Tap Cart icon at the upper right corner of the screen 3. Tap the item 4. Tap Note 5. Enter a note in the input field (1001 character) 6. Tap Apply | Note is not added to the order, the message 'Please, enter a note between 1 and 1000 characters' is displayed. | Failed | The app doesn't accept the note, but no clear error message is displayed.
TC-327 | Regression testing | Verify order details | Verify that the total cost of items and delivery fee are displayed in the cart. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon the the upper right corner of the screen 3. Verify that total cost is displayed 4. Verify that delivery fee is displayed | The total cost of items and delivery fee are displayed in the cart. | Passed
TC-328 | Regression testing | Verify cart persistence on the several devices | Verify that products previously added to the cart are displayed in the user's account on the other device. | 1. Mobile app MVP is ready for testing 2. Several devices or emulators for testing are ready 3. The application is installed on both devices 4. User is registered in the app 5. User is logged in to the app from both devices 6. The application is running on the both devices | 1. Open Skybot in Spaces app on one device 2. Tap Shop tab 3. Scroll down to browse catalog 4. Open any product item 5. Tap Add to cart button 6. Tap View to open cart 7. Open Skybot in Spaces app on the other device 8. Tap Cart icon at the upper right corner of the screen 9. Verify that all products from the first device are displayed | The products previously added to the cart are displayed in the user's account on the other device. | Failed | The cart is not dynamically synchronized across the devices. The updated cart is displayed on the other device only if the user closes the app completely and then reopens it. If the app is running in the background, the old cart view is displayed on the other device.
TC-329 | Retesting | Place the order with valid data | Verify that user can place an order online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon the the upper right corner of the screen 3. Tap Checkout 4. Tap Place a test order 5. Enter First name 6. Enter Last name 7. Enter a mobile phone 8. Select country from drop-down list 9. Enter address 10. Enter City (if not automatically filled) 11. Enter State/Region depending on the selected country 12. Enter zip code 13. Tap Continue Further steps are not currently available | User can purchase the product item via online form. User can fill out form with shipping address and pay for the order online. | Failed | User can't end purchase process online. Message that products are not available in the region is displayed. Infinite loading is displayed after closing of alert modal window. It disappears only after complete close of the app from the background running.
TC-330 | Retesting | Verify order tracking | Verify that updates on order status are provided. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. User has made a purchase | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Tap Orders 4. Verify that order's first status was Paid 5. Verify that order's second status is Shipped 6. Observe that information about Location of the Parcel is being updated 7. Verify that once an order is delivered a status Complete is set | Updates on order status including confirmation, payment, shipping, delivery, and completion are provided. | Skipped | Order placing is not currently available.
TC-331 | Regression testing | Place the order with empty required input fields | Verify that user can't place an order online if required data is not entered. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Product item is added to cart | 1. Open a mobile app 2. Tap Cart icon the the upper right corner of the screen 3. Tap Checkout 4. Tap Place a test order 5. Leave fields empty 6. Tap Continue | All input fields are required and can't be left empty to proceed the checkout process. Error message is displayed. | Passed
TC-332 | Retesting | Enter an invalid zip code in the order placing form | Verify that form doesn't accept an invalid zip code and displays an error message. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Cart is not empty | 1. Open Skybot in Spaces app 2. Tap Cart icon the the upper right corner of the screen 3. Tap Checkout 4. Tap Place a test order 5. Enter an invalid zip code in Zip/Postcode input field (non-digital characters) 6. Tap Continue | The form doesn't accept an invalid zip code and displays an error message. | Failed | Any symbol can be inputted in the zip code input field. No error message is displayed.
TC-333 | Regression testing | Enter a phone of invalid length | Verify that the form doesn't accept an invalid phone length and displays an error message. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Cart is not empty | 1. Open Skybot in Spaces app 2. Tap Cart icon the the upper right corner of the screen 3. Tap Checkout 4. Tap Place a test order 5. Enter an invalid phone in Phone input field (length <=4) 6. Tap Continue | The form doesn't accept an invalid phone and displays an error message. | Passed | The form doesn't accept an invalid phone and displays an error message.
TC-334 | Regression testing | Enter a phone of invalid format | Verify that the form doesn't accept an invalid phone format and displays an error message. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Cart is not empty | 1. Open Skybot in Spaces app 2. Tap Cart icon the the upper right corner of the screen 3. Tap Checkout 4. Tap Place a test order 5. Enter an invalid phone in Phone input field (with , or ;) 6. Tap Continue | The form doesn't accept an invalid phone and displays an error message. | Passed | The form doesn't accept an invalid phone and displays an error message.
TC-335 | Regression testing | Add a bank card | Verify that user can add a bank card for future purchases in personal account settings. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to Credit cards 4. Tap Credit cards 5. Tap Add 6. Enter a valid card number 7. Enter a valid expiration date 8. Enter a valid CVV 9. Enter a valid cardholder name 10. Tap Save | A bank card is successfully added to the profile and is displayed in Credit cards. | Passed | A bank card is successfully added to profile and is displayed in Credit cards.
TC-336 | Regression testing | Delete a bank card | Verify that user can delete a bank card in personal account settings. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to Credit cards 4. Tap Credit cards 5. Tap 3 horizontal dots at the right side of the card 6. Tap Delete card 7. Tap Yes in opened alert modal window | A bank card is successfully deleted from the profile and is not displayed in Credit cards. | Passed | A bank card is successfully deleted from the profile and is not displayed in Credit cards.
TC-337 | Regression testing | Enter an invalid card number | Verify that card number input field validates an entered card and allows only digits between 13 and 19 length. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to Credit cards 4. Tap Credit cards 5. Tap Add 6. Enter an invalid card number (12 digits) 7. Tap Save | Error message 'Enter a valid card number' is displayed. Card number is not accepted and can't be saved. | Passed | Error message 'Enter a valid card number' is displayed. Card number is not accepted and can't be saved.
TC-338 | Regression testing | Enter an invalid card expiration date | Verify that expire date input field validates an entered date and allows only valid date. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to Credit cards 4. Tap Credit cards 5. Tap Add 6. Enter an invalid month and year of the expire date 7. Tap Save | If user tries to enter digit higher than 12, second digit is entered as the first digit of the year. It the year is not valid, error message 'Enter a valid expiration date' is displayed. Date is not accepted and can't be saved. | Passed | If user tries to enter digit higher than 12, second digit is entered as the first digit of the year. It the year is not valid, error message 'Enter a valid expiration date' is displayed. Date is not accepted and can't be saved.
TC-339 | Regression testing | Enter an invalid card CVV | Verify that CVV input field validates an entered CVV and allows only 3 or 4 digits. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to Credit cards 4. Tap Credit cards 5. Tap Add 6. Enter an invalid CVV (2 digits) 7. Tap Save | Error message 'Enter a valid CVV' is displayed. CVV is not accepted and can't be saved. | Passed | Error message 'Enter a valid CVV' is displayed. CVV is not accepted and can't be saved.
TC-340 | Retesting | Sign up for a test drive with valid data | Verify that user above 12 y.o. can register for test drive online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Electric scooter first ride 4. Press button Book Now to open form 5. Enter a valid name in Name input field 6. Enter a valid phone number in Phone input field 7. Enter age >= 13 y.o. 8. Select Model from Model drop-down list 9. Select Date in calendar 10. Press Submit button | User is successfully registered for test drive online via special form. | Skipped | Functionality in the current version of the application is not yet implemented
TC-341 | Retesting | Sign up for a test drive as a user under 13 y.o | Verify that user under 13 y.o. can't register for test drive online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Electric scooter first ride 4. Press button Book Now to open form 5. Enter a valid name in Name input field 6. Enter a valid phone number in Phone input field 7. Enter age < 13 y.o. 8. Select Model from Model drop-down list 9. Select Date in calendar 10. Press Submit button | User is not registered for test drive online via special form. Age restriction is applied to form. | Skipped | Functionality in the current version of the application is not yet implemented
TC-342 | Retesting | Rent a scooter with valid data | Verify that user above 12 y.o. can register for scooter rent online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Scooter for rent 4. Press button Book Now to open form 5. Enter a valid name in Name input field 6. Enter a valid phone number in Phone input field 7. Enter age >= 13 y.o. 8. Select Model from Model drop-down list 9. Press Submit button | User is successfully registered for scooter rent online via special form. | Skipped | Functionality in the current version of the application is not yet implemented
TC-343 | Retesting | Rent a scooter as a user under 13 y.o. | Verify that user under 13 y.o. can register for scooter rent online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Scooter for rent 4. Press button Book Now to open form 5. Enter a valid name in Name input field 6. Enter a valid phone number in Phone input field 7. Enter age > 13 y.o. 8. Select Model from Model drop-down list 9. Press Submit button | User is not registered for scooter rent online via special form. Age restriction is applied to form. | Skipped | Functionality in the current version of the application is not yet implemented
TC-344 | Retesting | Sign up for warranty service | Verify that user can register for warranty service center repairment online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Service center repair 4. Press button Book Now to open form 5. Enter your First and Last name in input fields 6. Enter your phone number in Phone input field 7. Select Model from Model drop-down list 8. Enter your warranty code 9. Press button Submit | User is successfully registered for repairment online via special form. Valid warranty code is validated and accepted. | Skipped | Functionality in the current version of the application is not yet implemented
TC-345 | Retesting | Sign up for non-warranty service | Verify that user can register for non-warranty service center repairment online via special form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Services tab 3. Select Service center repair 4. Press button Book Now to open form 5. Enter your First and Last name in input fields 6. Enter your phone number in Phone input field 7. Select Model from Model drop-down list 8. Leave warranty code input field empty 9. Press button Submit | User is successfully registered for repairment online via special form. | Skipped | Functionality in the current version of the application is not yet implemented
TC-346 | Retesting | Verify rating system | Verify that a 1-5 star rating system is implemented. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Tap any product item 4. Scroll down the opened screen 5. Tap Leave a review 6. Verify that 1 to 5 stars are available to rate a product | 1-5 star rating system is implemented. Min allowable rate is 1 star, max - 5 stars. | Skipped | Functionality in the current version of the application is not yet implemented
TC-347 | Retesting | Publish a review as an unregistered user | Verify that unregistered users can't leave a review. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is not registered in the app | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Tap any product item 4. Scroll down the opened screen 5. Tap Leave a review 6. Verify that message 'Please, Sign up or Log in to leave a review' is displayed. | User can't leave a review without logging in the account. | Skipped | Functionality in the current version of the application is not yet implemented
TC-348 | Retesting | Publish a review with text fields filled | Verify that a registered user can leave a review with rating. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Tap any product item 4. Scroll down the opened screen 5. Tap Leave a review 6. Select stars in Add a rating section 7. Enter a title in a Review title 8. Enter a review in a Review 9. Tap Publish | Review is published and displayed on the page. Rating is saved accurately. | Skipped | Functionality in the current version of the application is not yet implemented
TC-349 | Retesting | Publish a review with attached photos | Verify that a registered user can leave a review with rating, and attach a photo. Extensions: jpg, png. Size: <= 5Mb | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Shop if this tab is not opened 3. Tap any product item 4. Scroll down the opened screen 5. Tap Leave a review 6. Select stars in Add a rating section 7. Enter a title in a Review title 8. Enter a review in a Review 9. Tap photo icon to attach a photo 10. Select a photo from gallery 11. Tap Publish | Review with media files are published and displayed on the page. Rating is saved accurately. Photos have initial quality and may be expanded for better view. | Skipped | Functionality in the current version of the application is not yet implemented
TC-350 | Regression testing | Verify YouTube videos integration | Verify that videos from YouTube are available from the app, and users can access web portal videos directly on YouTube. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Videos tab 3. Tap any video 4. Tap Play 5. Ensure that YouTube button is displayed on the video window 6. Tap the YouTube button 7. Verify that video is published on YouTube | Videos displayed in the app are integrated with YouTube. It is possible to watch these videos directly from YouTube. | Passed
TC-351 | Regression testing | Open video in YouTube app | Verify that user can open a video in YouTube app without launching the app. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app. 2. Tap Videos tab. 3. Verify that videos are displayed on the screen 4. Select any video 5. Tap "Watching on YoTube" button in the player window. | Video can be played directly in YouTube app. Users without Skybot account don't need to register in order to watch video. | Passed
TC-352 | Regression testing | Play video while music is playing | Verify that music is stopped if video is being started playing. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Music is playing on the device | 1. Open Skybot in Spaces app 2. Verify that videos are displayed on the screen 3. Select any video 4. Tap Play | Music is automatically stopped when video starts playing. Only sound from video is played. | Passed | Music is automatically stopped when video starts playing. Only sound from video is played.
TC-353 | Retesting | Send message via online chat | Verify that user can send a message to Skybot online chat, and the message will be delivered. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap Chat icon in the lower menu bar 3. Tap New Message 4. Enter test on Message Skybot input field 5. Tap Send 6. Verify that message is sent 7. Verify that response is received | Messages from user are received by Skybot team. User receives a response from Skybot. | Failed | User doesn't receive a response from Skybot.

## UI and Navigation check
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Type | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-401 | Retesting | Verify brand recognition | Verify that the mobile app design corresponds to the web portal. Mobile app is visually recognised as Skybot. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Visually inspect logo 3. Visually inspect app color palette 4. Ensure that app's sections correspond to the web portal's | Consistency between the mobile app and web portal UI is maintained. | Failed | The logo in the app differs from the portal version. The main color used for the mobile app differs from the color used in the web portal: #281A39 in the web portal and #BF42BA in the mobile app.
TC-402 | Regression testing | Verify app icon | Verify that the app icon is simple, has a good resolution, conforms with the app, and looks good in square form. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | 1. Visually inspect app icon on the Home screen or App library | App icon design doesn't go beyond the edges, the text is easy to read, design is simple and minimalistic. | Passed | App icon design doesn't go beyond the edges, the text is easy to read, design is simple and minimalistic.
TC-403 | Retesting | Verify logo | Verify that a logo has a transparent background, and has a link to the main page. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Visually inspect the logo 3. Tap Skybot logo at the upper left corner of the screen | The logo has a transparent background and redirects the user to the main page. | Failed | The logo has a border, partially overlaps the header photo, and doesn't redirect the user to the main page.
TC-404 | Retesting | Verify text visibility | Verify that all texts are visible, and truncated text can be expanded. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Navigate across the menu tabs 3. Browse catalog 4. Browse PDPs of each product item 5. Verify that all texts can be read by the user | Texts have sufficient contrast levels and can be easily read by the user. All truncated texts can be expanded to view the full string. | Failed | Long text in some corner badges is truncated, can't be expanded, and is not written fully on the PDP.
TC-405 | Regression testing | Verify font style | Verify that font style conforms to the app subject, and size makes reading convenient. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Navigate across the menu tabs 3. Browse catalog 4. Browse PDPs of each product item 5. Verify that text corresponds to the app subject | Font style, weight, and size are selected accurately, making reading easy and user-friendly. | Passed | Font style, weight, and size are selected accurately, making reading easy and user-friendly.
TC-406 | Regression testing | Verify icons | Verify that all icons used in the app convey the app's features, and have label texts. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Visually inspect all icons: in the bottom navigation bar, in My Activity section of My Profile, in site header 3. Verify that they convey the app's functionality | Icons maintain visual consistency across all interface icons, have a label text, and the weights of interface icons and adjacent text match. | Passed | Icons maintain visual consistency across all interface icons, have a label text, and the weights of interface icons and adjacent text match.
TC-407 | Regression testing | Navigate across Skybot menu tabs | Verify that user can navigate across Skybot via menu. Menu is easy to reach and leads to correct screens. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | 1. Open Spaces app 2. Go to Skybot site 3. Tap menu tabs under the header of site | All menu tabs can be opened by tap. Accurate sections are displayed for each tab. | Passed
TC-408 | Regression testing | Navigate across lower app bar | Verify that user can navigate across Skybot via menu. Menu is easy to reach and leads to correct screens. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | 1. Open Spaces app 2. Go to Skybot site 3. Tap menu icons in the lower app navigation bar | Navigation bar leads to the accurate screens. All icons in the bar are clickable. | Passed
TC-409 | Regression testing | Verify buttons and links | Verify that all buttons and links are clickable and lead to correct screens or open correct sections and pages. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device | 1. Open Spaces app 2. Go to Skybot site 3. Tap all buttons on different Skybot screens | All buttons and links work accurately, lead to the correct sections and open accurate screens. | Passed
TC-410 | Retesting | Verify elements alignment | Verify that elements are aligned accurately and don't overlap each other. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Visually each screen's elements alignment | Elements don't overlap each other and can be easily accessed by the user. All elements are aligned accurately. | Failed | Text of the technical description for products is not aligned accurately
TC-411 | Regression testing | Verify interactive elements animation | Verify that all interactive elements are animated when user taps them. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap any button you find on the screen 3. Verify that buttons have animation 4. Tap form's input fields 5. Verify that fields are highlighted and cursor appears | Interactive elements are responsive and react to user's taps. | Passed
TC-412 | Retesting | Verify display for different screen orientations | Verify that screen rotation is locked everywhere except for photo and video content. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Screen rotation is enabled in device settings | 1. Open a mobile app 2. Rotate a device to the landscape orientation 3. Verify that rotation is locked 4. Go to Shop tab 5. Tap any product item in the catalog 6. Tap photo to open it in a full screen mode 7. Rotate phone to the landscape orientation 8. Rotate phone to the portrait orientation back 9. Close photo window 10. Tap arrow at the upper left corner of the screen to return to main screen 11. Tap Video tab 12. Tap any video to play 13. Rotate phone to the landscape orientation | Landscape orientation is available for app. | Failed | Landscape orientation is available only for photo and videos. It is locked for other screens.
TC-413 | Regression testing | Verify keyboard display and type | Verify that keyboard automatically expands when user tap input fields, and keyboard type corresponds to the input field type. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open a mobile app 2. Tap form's input fields (sign up/login/checkout/search bar) 3. Verify that keyboard opens automatically 4. Verify that keyboard is adaptive to data that should be entered | Keyboard type corresponds to the input field type. | Passed
TC-414 | Regression testing | Verify color scheme | Verify that primary, secondary, trinity (optional), and neutral colors are used in the app; confirm and error messages are displayed in green and red respectively. Verify that colors look good in both light and dark mode. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Navigate across the site 3. Verify that there are max 3 different colors 4. Verify that there is 1 primary color | An accurate color scheme is used in the app. Generally accepted colors are used for confirm and error messages. The app doesn't use more than 3 different not neutral colors (tones are allowed). Sufficient contrast is applied to both white and dark themes. | Passed | An accurate color scheme is used in the app. Generally accepted colors are used for confirm and error messages. The app doesn't use more than 3 different not neutral colors (tones are allowed). Sufficient contrast is applied to both white and dark themes.
TC-415 | Regression testing | Switch light/dark mode | Verify that user can switch light/dark mode in the app. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to App display 4. Tap App display 5. Tap Light mode if Dark is used OR Dark mode if Light is used 6. Tap Save at the upper right corner of the screen 7. Tap Restart in the opened alert modal window | Light and dark modes are available in the app. User can change it in the settings without changing color mode in the device settings. | Passed | After restarting the application, the color scheme changed, but the application language switched from English to Ukrainian - the language of the system.
TC-416 | Regression testing | Verify that text size adapts to the device's one | Verify that users who prefer larger text size see the larger text in the app. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. Text size enlarged in the user's device settings | 1. Open Skybot in Spaces app 2. Ensure that text size is enlarged 3. Verify that text is displayed accurately even if the font size is enlarged | The app conveys the text size change in the device's settings. Text is displayed correctly if it is enlarged. | Passed
TC-417 | Regression testing | Verify radio buttons | Verify that radio button is used where only one item can be selected from a list. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application's bottom navigation bar 3. Scroll to App display 4. Tap App display 5. Verify radio buttons in accessible mode options | The radio button is used where only one item can be selected from a list. Selected option is highlighted with color. | Passed | The radio button is used where only one item can be selected from a list. Selected option is highlighted with color.
TC-418 | Regression testing | Verify that app's language conforms with the device's one | Verify that the language in the app is equal to the language used on the device. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. The application wasn't opened yet | 1. Open Skybot in Spaces app 2. Verify that app's language corresponds to the language used by the device. | The app uses the first language that it supports from Language preference in the device settings. | Passed
TC-419 | Retesting | Verify the app's language accuracy | Verify that all texts are displayed in the selected language. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap Shop if this tab is not opened 3. Scroll down the screen 4. Tap See all button 5. Inspect product items' language 6. Navigate across other tabs: Home, Schedule, Services, Video | All texts are displayed in the selected language. | Failed | For the English language some descriptions of the products are displayed in Ukrainian.
TC-420 | Retesting | Change app language | Verify that app's texts are translated to the selected language. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Tap My Profile icon at the right side of the application bottom navigation bar 3. Scroll to App language 4. Tap App language 5. Select any other language 6. Tap Save 7. Tap Restart in the opened alert modal window 8. Verify that texts are displayed in the other language | The app's texts are translated to the selected language. | Failed | Partial product names and descriptions don't change regardless the selected language.
TC-421 | Retesting | Verify photos | Verify that images are high-resolution, have a similar design, and can be zoomed in/out by pinch gestures. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Open Skybot in Spaces app 2. Navigate across the menu tabs and inspect photos on these screens 3. Tap Shop 4. Scroll down the screen 5. Tap See all button 6. Inspect displayed photos 7. Open each PDP 8. Scroll all photos for each PDP | Images are of good quality, have a similar design, and can be zoomed in/out by pinch gestures. | Failed | Photos in the Shop catalog are visually inconsistent. Some products are displayed on the white background, others on the real-world background.

## Compatibility check
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Type | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-501 | Retesting | Verify compatibility with different IOS versions | Verify that the app can be launched without crashes and freezes, functionality is available and works as expected regardless the IOS version. Supported IOS versions displayed in App Store: 14.0 and higher | 1. Mobile app MVP is ready for testing 2. Devices with different IOS versions are ready for testing | 1. Install the app on the devices with different IOS versions 2. Launch the app 3. Sign up or log in personal account 4. Execute functional tests 5. Verify that app's performance is consistent across different OS versions | The application works without crashes and delays on different IOS versions. | Skipped | Real IOs devices or emulators are not available.
TC-502 | Regression testing | Verify compatibility with different Android versions | Verify that the app can be launched without crashes and freezes, functionality is available and works as expected regardless the IOS version. Supported Android versions displayed in Google Play: 7.0 and higher | 1. Mobile app MVP is ready for testing 2. Devices with different Android versions are ready for testing | 1. Install the app on the devices with different IOS versions 2. Launch the app 3. Sign up or log in personal account 4. Execute functional tests 5. Verify that app's performance is consistent across different OS versions | The application works without crashes and delays on different Android OS versions. | Passed
TC-503 | Regression testing | Verify compatibility with screen resolutions | Verify that the app is displayed without visual defects regardless the screen resolutions. | 1. Mobile app MVP is ready for testing 2. Devices with different screen resolutions are ready for testing 3. The application is installed on the device 4. User is registered in the app 5. User is logged in | 1. Install the app on the devices with different Android versions 2. Launch the app 3. Sign up or log in personal account 4. Navigate across the app 5. Inspect the display of app's elements | App screens are displayed accurately on different screen resolutions. No visual defects are present. | Passed
TC-504 | Retesting | Verify compatibility with different IOS devices | Verify that the app can be launched without crashes and freezes, functionality is available and works as expected regardless the IOS device. | 1. Mobile app MVP is ready for testing 2. Different IOS devices are ready for testing | 1. Install the app on the devices with different IOS versions 2. Launch the app 3. Sign up or log in personal account 4. Execute functional tests 5. Verify that app's performance is consistent across different devices | The application works without crashes and delays on different IOS devices. | Skipped | Real IOs devices are not available.
TC-505 | Regression testing | Verify compatibility with different Android devices | Verify that the app can be launched without crashes and freezes, functionality is available and works as expected regardless the Android device. | 1. Mobile app MVP is ready for testing 2. Different Android devices are ready for testing | 1. Install the app on the devices with different IOS versions 2. Launch the app 3. Sign up or log in personal account 4. Execute functional tests 5. Verify that app's performance is consistent across different devices | The application works without crashes and delays on different Android devices. | Passed

## Interaction with the server
|  |  |  | Build | Skybot Mobile App version 2.0
Environment
|  |  |  | Platform |  | OS version | Screen resolution
|  |  |  | Mobile | Samsung Galaxy S10+ | Android 12 | 2280 x 1080
[5 empty] | Samsung Galaxy S21 Ultra | Android 14 | 3200 x 1440
ID | Type | Summary | Description | Preconditions | Step actions | Expected Results | Actual Result | Note / Link to bug report
TC-601 | Regression testing | Verify app's work with mobile connection. | Verify the application performance via mobile internet connection. | 1. A device or emulator for testing is ready | 1. Open Skybot in Spaces app | The app works accurately and fast via mobile connection. The response is received within 3 seconds. |  | The app works accurately and fast via LTE. The response is received within 3 seconds.
|  |  |  | 2. The application is installed on the device | 2. Navigate across the app
|  |  |  | 3. User is registered in the app | 3. Execute functional tests |  | Passed
|  |  |  | 4. The device is connected via mobile connection. | 4. Verify that the app performance is within 3 seconds
TC-602 | Regression testing | Verify app's work with Wi-Fi | Verify the application performance via Wi-Fi connection. | 1. A device or emulator for testing is ready | 1. Open Skybot in Spaces app | The app works accurately and fast via Wi-Fi. The response is received within 3 seconds. |  | The app works accurately and fast via Wi-Fi. The response is received within 3 seconds.
|  |  |  | 2. The application is installed on the device | 2. Navigate across the app
|  |  |  | 3. User is registered in the app | 3. Execute functional tests |  | Passed
|  |  |  | 4. The device is connected via Wi-Fi | 4. Verify that the app performance is within 3 seconds
TC-603 | Regression testing | Switching the connection from Wi-Fi to a mobile connection | Verify that the app continues working and doesn't restart if the network connection has been changed. | 1. Mobile app is ready for testing | 1. Open Skybot in Spaces app | The app continues working and doesn't restart if the network connection has been changed. User can proceed the current action in the app. |  | The app continues working and doesn't restart if the network connection has been changed. User can proceed the current action in the app.
|  |  |  | 2. A device or emulator for testing is ready | 2. Go to Shop tab menu
|  |  |  | 3. The application is installed on the device | 3. Tap any product item
|  |  |  | 4. User is registered in the app | 4. Switch from Wi-Fi to cellular connection |  | Passed
|  |  |  | 5.User is logged in | 5. Add a product to cart
6. Tap Cart icon at the upper right corner of the header
7. Verify that app is working smoothly and no delays occur
TC-604 | Regression testing | Turn off connection while using the app | Verify that user is clearly informed that the Internet connection was lost. | 1. Mobile app is ready for testing | 1. Open Skybot in Spaces app | The user is clearly informed that the Internet connection was lost. The app doesn't freeze or close. |  | The user is clearly informed that the Internet connection was lost. The app doesn't freeze or close.
|  |  |  | 2. A device or emulator for testing is ready | 2. Tap Cart icon at the upper corner of the screen
|  |  |  | 3. The application is installed on the device | 3. Tap Checkout |  | Passed
|  |  |  | 4. User is registered in the app | 4. Verify warning message is displayed in the app
5. User is logged in
6. Cart is not empty
TC-605 | Regression testing | Launch app without Internet connection | Verify that the app launches without Internet connection and warning message is displayed. | 1. A device or emulator for testing is ready | 1. Open Skybot in Spaces app | The app launches and Skybot can be opened without Internet connection. Informational message "You're offline. Please, connect to the network" is displayed. |  | The app launches and Skybot can be opened without Internet connection. Informational message "You're offline. Please, connect to the network" is displayed.
|  |  |  | 2. The application is installed on the device | 2. Verify that limited Skybot is launched and displayed | The message "You're offline. Screen will refresh once you're back online" is displayed on the main screen of the application.
|  |  |  | 3 User is registered in the app | 3. Verify that user is notified that there is no Internet connection |  | Passed
4.Wi-Fi or mobile Internet connection is disabled
TC-606 | Regression testing | Network Traffic Analysis | Checking the connection and the correctness of the interaction between the application and the server, Checking the transmitting and receiving data. | 1. A device or emulator for testing is ready | 1.Open the "PCAPdroid nettwork monitor" app. | The application interacts with the server. Successful HTTPS requests are made through port 443. Successful DNS requests are made through port 53.
|  |  |  | 2. The "Spaces: Follow Businesses" app is installed on the device | 2.On the "Status" tab, in the "Target apps" section, select the "Spaces by Wix" application. |  | Passed
|  |  |  | 3. The "PCAPdroid nettwork monitor" is installed on the device | 3.Tap the "Ready" button to start minitoring.
4.Open the Skybot in Spaces app and use it.
5.Open the "PCAPdroid nettwork monitor" and tap stop monitoring button.
5.On the "Connections" tab look at the "Spaces by Wix" app traffic.
TC-607 |  | Verify the https usage | Verify that https with 443 port is used by the app. | 1. Mobile app MVP is ready for testing 2. A device or emulator for testing is ready 3. The application is installed on the device 4. User is registered in the app 5. User is logged in 6. The "PCAPdroid nettwork monitor" is installed on the device/ | 1. Open Skybot in Spaces app 2. Navigate across the app 3. Browse catalog 4. Add a product to cart 5. Execute a Checkout process 6. Inspect the response codes in app traffic inspect app | The app uses https, https port is 443. | Passed | The app uses https, https port is 443.